## Consecutive
PROJECT TIMELINE TEMPLATE
PROJECT TITLE |  | [Project's title]
PROJECT MANAGER |  | [Project Manager's name]
PHASE |  |  | DETAILS | Q3 | [13 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2
|  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN
| PROJECT WEEK: |  | Enter the date of the first Monday of each month --> | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30
1 | Major Program Milestones |  | On Ground Testing | bar: OCT 7 to OCT 14
Motor Test | bar: NOV 18 to DEC 2
In Air EMI Test | bar: MAR 10
Final Testing | bar: MAY 5 to MAY 12
Competition
2 | Mechanical |  | Design Motor Mount | bar: SEP 30 to OCT 14
Manufature Mount & Install Motor | bar: OCT 21 to NOV 11
Test New Motor In Air | bar: NOV 18
Test Phoenix on Ground | bar: NOV 25 to DEC 2
Design Comp Mount | bar: JAN 13 to JAN 20
Manufature & Install New Mount and Harness | bar: FEB 17 to FEB 24
In Air EMI Test | bar: MAR 10
Design Battery Removal System +EMI Mit | bar: MAR 17
Manufacture & Install Battery Removal System + EMI Mit | bar: MAR 24 to APR 7
Full Vehicle Test | bar: MAY 5 to MAY 12
3 | Electrical |  | Design New Motor Harness | bar: SEP 30 to OCT 14
Manufacture & Install Motor Harness | bar: OCT 21 to NOV 11
Test New Motor in Air | bar: NOV 18
Test Phoenix on Ground | bar: NOV 25 to DEC 2
Design New Primary Harness | bar: JAN 13 to FEB 3
Manufature & Install New Harness | bar: FEB 10 to FEB 24
In Air EMI Test | bar: MAR 10
Design Battery Removal System + EMI Mit | bar: MAR 17
Manufacture & Install Battery Removal System + EMI Mit | bar: MAR 24 to APR 7
Full Vehicle Test | bar: MAY 5 to MAY 12
4 | Software |  | On Ground Data Collection | bar: OCT 7 to OCT 14
Develope In Sim | bar: OCT 21 to OCT 28
Develope Motor Control Software | bar: NOV 4 to NOV 11
Test Motor in Air | bar: NOV 18
Test Phoenix on Ground | bar: NOV 25 to DEC 2
Tune PID | bar: JAN 13 to JAN 20
In Air EMI Test | bar: MAR 10
Full Test | bar: MAY 5 to MAY 12
5 | Extra |  | Extra
Extra
Extra

## Concurrent
PROJECT TIMELINE TEMPLATE
PROJECT TITLE |  | [Project's title]
PROJECT MANAGER |  | [Project Manager's name]
PHASE |  |  | DETAILS | Q3 | [13 empty] | Q4 | [12 empty] | Q1 | [12 empty] | Q2
|  |  |  | JUL |  |  |  |  | AUG |  |  |  | SEP |  |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  |  | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN
| PROJECT WEEK: |  | Enter the date of the first Monday of each month --> | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30
1 | Major Program Milestones |  | On Ground Testing | bar: OCT 7 to OCT 14
Motor Test | bar: NOV 18 to DEC 2
In Air EMI Test | bar: FEB 10
Final Testing | bar: MAR 24 to APR 7; MAY 5 to MAY 12
Competition
2 | Mechanical |  | Design Motor Mount | bar: SEP 30 to OCT 14
Manufature Mount & Install Motor | bar: OCT 21 to NOV 11
Test New Motor In Air | bar: NOV 18
Test Phoenix on Ground | bar: NOV 25 to DEC 2
Design Comp Mount | bar: NOV 4 to DEC 2; JAN 13 to JAN 20
Manufature & Install New Mount and Harness | bar: JAN 13 to FEB 3
In Air EMI Test | bar: FEB 10
Design Battery Removal System +EMI Mit | bar: JAN 13 to FEB 24
Manufacture & Install Battery Removal System + EMI Mit | bar: FEB 24; MAR 10 to MAR 17
Full Vehicle Test | bar: MAR 24 to APR 7; MAY 5 to MAY 12
3 | Electrical |  | Design New Motor Harness | bar: SEP 30 to OCT 14
Manufacture & Install Motor Harness | bar: OCT 21 to NOV 11
Test New Motor in Air | bar: NOV 18
Test Phoenix on Ground | bar: NOV 25 to DEC 2
Design New Primary Harness | bar: NOV 4 to DEC 2; JAN 13 to JAN 20
Manufature & Install New Harness | bar: JAN 13 to FEB 3
In Air EMI Test | bar: FEB 10
Design Battery Removal System + EMI Mit | bar: NOV 4 to DEC 2; JAN 13 to FEB 24
Manufacture & Install Battery Removal System + EMI Mit | bar: FEB 24; MAR 10 to MAR 17
Full Vehicle Test | bar: MAR 24 to APR 7; MAY 5 to MAY 12
4 | Software |  | On Ground Data Collection | bar: OCT 7 to OCT 14
Update sim | bar: OCT 14 to OCT 28; DEC 2
Line detection+new planner | bar: OCT 21 to DEC 2
Update PIR for new motor controller
Test Motor in Air | bar: DEC 2
Test Phoenix on Ground | bar: NOV 25 to DEC 2
Tune PID | bar: JAN 13 to JAN 20
Line detecton and planner iteration | bar: JAN 13 to MAR 17
In Air EMI Test | bar: FEB 10
Full Test | bar: MAR 24 to APR 7; MAY 5 to MAY 12
5 | Extra |  | Extra
Extra
Extra